## Project Tracking
PROJECT TRACKING SHEET SUMMARY
| Total Projects |  | Strategic Projects |  |  | ROI
| On Going |  | Improvement Projects
| Planned |  | Cost Efficiency Projects
| Delayed |  | Innovation Projects
Departments Engaged
List of Cost Efficiency Projects
N. | Project Title | Project Owner | Department | Status | Cost Savings (SAR)
1 | Reducing Inappropriate CT studies and minimizing radiation exposure | Dr. Ahmed Nafea | Radiology | On Going | Pending in Data Collection Phase
2 | Operational cost reduction in Mpox diagnosis: Lean approach | Ms. Jawaher Aldabaan | Infection control | On Going | 310005
3 | Accuracy in TB Cases | Ms. Jawaher Aldabaan | Infection control | On Going | Pending in Calculating avoidant cost
4 | Reducing Average Length of stay from 5.5 to 3.5 Days within 6 months At Al Iman General Hospital | Mr. Hani | Inpatient dept | On Going | 4341610
5 | FAST-Track Rehab: Reducing Admission Delays to < 1.5 days | Dr. Enas Makawi | Rehab | Completed By 2025 DEC. | 4373600
6
7
8
9
10
11

## Cost Efficiency Projects (hidden)
COST EFFICIENCY PROJECTS TRACKING SHEET
Sheet Under responsibility of Ms. Rahaf
[14 empty] | STATUS KEY | PRIORITY KEY
[14 empty] | On Hold | Low
[14 empty] | Not Yet Started | Medium
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI |  |  | In Progress | High
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual | Complete
Reducing Inappropriate CT studies and minimizing radiation exposure - Project Owner Dr. Ahmed Nafea | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | RISK KEY
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | On Track
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | At Risk
Critical
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %

## Hospital Director Projects
PROJECTS TRACKING SHEET
Sheet Under responsibility of Ms. Rahaf
[15 empty] | STATUS KEY | PRIORITY KEY
[15 empty] | On Hold | Low
[15 empty] | Not Yet Started | Medium
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI As of April 2026 |  |  | In Progress | High
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Blockers | Baseline | Targeted | Actual | Complete
Enhancing the patient experience in outpatient departments (OPD) - Project Owner: Mr. Jahz Almotairy | [9 empty] | #DIV/0! |  | Press ganey |  |  | Delayed
Not Yet Started | On Track | Low | 2026-07-08 | 2026-09-30 | 82 | زيادة التوعية بالرقم 19910 | مدير العيادات مديرة التمريض للعيادات الخارجية | بوسترز و عمل ورشات عمل مع التمريض | تحسين سهولة التواصل مع العيادات وتقليل بلاغات 937 | % |  |  | > 85%
Not Yet Started | On Track | High | 2026-07-08 | 2026-09-30 | 82 | تحسين تواصل الاطباء | تجربة المريض الإدارة الطبية | Details of task here | 0% بلاغات سوء معاملة محق وتقليل البلاغات الناتجة عن ضعف التواصل وتحسين التواصل مع الطبيب | % |  | سوء المعاملة المحقة |  |  | RISK KEY
Not Yet Started | On Track | Medium | 2026-07-08 | 2027-01-01 | 173 | Task | مدير نموذج الرعاية الصحية | تقليل عدد الزيارات لإتاحة المواعيد ولتقليل المواعيد الإضافية وتقليل الضغط على العيادات | إعطاء المريض الوقت الكافي – توفر المواعيد | % |  |  | 0 |  | On Track
Not Yet Started | On Track | High | 2026-07-08 | 2026-09-30 | 82 | تحسين تواصل التمريض | إدارة التمريض | ورشات عمل وتعليم مستمر للتمريض | تعزيز التواصل الفعال والتعاطف مع المريض | % |  | تواصل فعال (طبيب – تمريض) As of July 2026 |  |  | At Risk
Delayed | Critical | High | 2026-07-09 | 2027-01-01 | 172 | أجهزة الخدمة الذاتية والاستدعاء | إدارة الصحة الرقمية | تفعيل الاجهزة وعمل اللازم من التدريب | تقليل الانتظار وتحسين تجربة المريض وتقليل التنقلات للتمريض من وإلى العيادة خلال الاستدعاء | % |  |  | > 90% |  | Critical
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI As of April 2026
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Blockers | Baseline | Targeted | Actual
Enhancing communication in the Emergency Department (ED) - Project Owner: Mr. Jahz Almotairy | [9 empty] | #DIV/0! |  | تأخير استقبال / خدمة المريض في المنشأة الصحية
Not Yet Started | On Track | High | 2026-07-08 | 2026-12-31 | 173 | ورشة عمل خاصة | تجربة المريض إدارة التمريض | تفعيل دور منسقين الطوارئ وحل الإشكاليات الواردة في التقارير | توعية الموظفين بالمهام المطلوبة | % |  | 39 بلاغ |  | 39 بلاغ
Not Yet Started | On Track | High | 2026-07-08 | 2026-12-31 | 173 | السياسات | إدارة الموارد الذاتية الجود | مراجعة السياسات الخاصة بالموارد الذاتية | وضوح الإجراءات وتسهيلها | % |  | عدم وجود اهتمام باحتياجات المريض وتقصير في الخدمة
Not Yet Started | On Track | High | 2026-07-08 | 2027-01-01 | 173 | السياسات | الإدارة الطبية الجودة | مراجعة سياسات استقبال حالات النساء والولادة | تحسين رحلة المريض | % |  | 24 بلاغ |  | 24 بلاغ
Not Yet Started | On Track | High | 2026-07-09 | 2027-01-02 | 173 | التقارير | الإدارة الطبية | تسريع إجراءات كتابة تقارير الاصابات | تحسين رحلة المريض | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI As of April 2026
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Blockers | Baseline | Targeted | Actual
Compliance with Sick Leave Procedures - Project Owner: Mr. Jahz Almotairy | [9 empty] | #DIV/0! |  | شكاوي الاجازات المرضية (حضوري,937,19910)
Not Yet Started | On Track | High | 2026-07-08 | 2026-12-31 | 173 | متابعة دورية للاجازات | التقارير الطبية | المراجعة اليومية من قبل التقارير الطبية لإعادة ربط الاجازات | تقليل البلاغات | % |  | 99 |  | 99
Not Yet Started | On Track | Medium | 2026-07-08 | 2026-12-31 | 173 | منسق تقارير | الإدارة الطبية | توفير منسق لعمل تقرير اسبوعي بالتفاصيل يرسل إلى الإدارة الطبية | توعية الموظفين بأثر المشكلة وانعكاسه على المرضى | %
Not Yet Started | On Track | High | 2026-07-08 | 2026-12-31 | 173 | توعية بأهمبة الاجازات المرضية | الإدارة الطبية | عمل الجلسات التوعوية مع الاطباء | تقليل الشكاوى | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI As of April 2026
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Blockers | Baseline | Targeted | Actual
إحسان للتنويم Project Owner: Mr. Jahz Almotairy | [9 empty] | #DIV/0! |  | سوء معاملة وسوء تواصل
Not Yet Started | On Track | Medium | 2026-07-08 | 2026-12-31 | 173 | متابعة يومية | تجربة المريض | المرور اليومي للمرضى المنومين وقياس التواصل رصد سوء المعاملة والتواصل | 0% بلاغات سوء معاملة وتقليل البلاغات الناتجة عن ضعف التواصل | % |  |  | 0
Not Yet Started | On Track | Medium | 2026-07-08 | 2026-12-31 | 173 | متابعة يومية | تجربة المريض | رصد عدم المرور اليومي وعدم التجاوب (أطباء – تمريض) | تقليل التواصل السلبي مع الأطباء والتمريض | % |  | تطبيق عناصر احسان
Not Yet Started | On Track | Medium | 2026-07-08 | 2026-12-31 | 173 | إحسان | تجربة المريض | تطبيق عناصر احسان في التنويم | تعزيز التواصل الفعال والتعاطف مع المريض | % |  |  | 90 %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE |  | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! |  | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %

## Strategic Projects (hidden)
STRATEGIC PROJECTS TRACKING SHEET
Sheet under responsibility of Ms. Atheer
[14 empty] | STATUS KEY | PRIORITY KEY
[14 empty] | On Hold | Low
[14 empty] | Not Yet Started | Medium
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI |  |  | In Progress | High
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual | Complete
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here | [5 empty] | RISK KEY
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | On Track
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | At Risk
Critical
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %

## Improvement Projects (hidden)
IMPROVEMENT PROJECTS TRACKING SHEET
Sheet Under responsibility of Dr. Bedir
[14 empty] | STATUS KEY | PRIORITY KEY
[14 empty] | On Hold | Low
[14 empty] | Not Yet Started | Medium
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI |  |  | In Progress | High
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual | Complete
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here | [5 empty] | RISK KEY
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | On Track
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | At Risk
Critical
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %

## Innovation Projects (hidden)
INNOVATION PROJECTS TRACKING SHEET
Sheet under responsibility of Ms. Reema
[14 empty] | STATUS KEY | PRIORITY KEY
[14 empty] | On Hold | Low
[14 empty] | Not Yet Started | Medium
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI |  |  | In Progress | High
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual | Complete
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here | [5 empty] | RISK KEY
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | On Track
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | % |  |  |  | At Risk
Critical
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
PROJECT DETAILS | [8 empty] | DELIVERABLES |  | KPI
STATUS | RISK | PRIORITY | START DATE | END DATE | DURATION | TASK NAME | ASSIGNEE | DESCRIPTION | DELIVERABLE | % DONE | Baseline | Targeted | Actual
Project Name - Project Owner | [9 empty] | #DIV/0! | (KPI Name) As of (date)
On Hold | On Track | High | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
Not Yet Started | On Track | Low | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here
In Progress | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %
Complete | On Track | Medium | 2026-07-02 | 2026-07-02 | 0 | Task |  | Details of task here |  | %